## Project Management Plan Q1 - 21
Week | Tasks | Estimation
2021-01-18 | Create a Github Repo | 30 min
| Create a Spreadsheet | 30 min
| Create a Trello Board | 30 min
| added ssh keys to github | 30 min
| prepare python files and test them locally with make | 1 h
2021-01-25
2021-02-01
2021-02-08
2021-02-15
2021-02-22
2021-03-01
2021-03-08
2021-03-15
2021-03-22
2021-03-29
2021-04-05

## Final Project Plan 2021
Week | Tasks | Estimation
19/11/2020 | Create The Cloud-Based Development Environment | 30 mins
19/11/2020 | Create Project Scaffolding | 2hrs
19/11/2020 | Local Test | 1hrs
21/11/2020 | Config GitHub Actions | 1 hrs
22/11/2020 | Continuous Delivery to Azure | 5 hrs
25/11/2020 | Write Documentation | 10 hrs
28/11/2020 | Demo Work with Video | 8 hrs